## Slide 1
Stakeholder | Role (Related to project) | Involvement | Impact | Power or Influence (H/M/L) | Interest (H/M/L) | Engagement
Director of product | Project sponsor | Participation: Signs off on high-level decisions and acts as an escalation resource for the team; highly invested but not involved day-to-day. Resources: Decision-making authority, strategic corporate vision, and organizational influence. | Impact on Needs: Hits high-level product expansion targets and drives company growth. Success validates their strategic choices. Potential Resistance: None expected. They are the project sponsor and fully back the launch. | High (H) | Medium (M) | Frequency: Regularly (weekly or biweekly at key milestones). Form: High-level project status reports, milestone sign-offs, and brief alignment meetings to review high-level decisions without overwhelming them with daily operations.
Landscape Designer/Web Designer | Project team member | Participation: Actively builds the web infrastructure and shapes the plant service design. Resources: Technical web design skills, deep botanical/plant knowledge, and strong cross-departmental internal relationships. | Impact on Needs: Highly affected. The launch may force their dual role to pivot away from traditional landscape design toward managing this new service. Potential Resistance: High Risk. If they are unhappy about their daily responsibilities changing, they might resist. Because they have strong internal relationships across the company, their lack of buy-in could easily influence others. | High (H) | High (H) | Frequency: Daily / Highly frequent. Form: Frequent updates through daily stand-ups, direct collaboration chats, and 1-on-1 consultations. This keeps their technical tasks on track and allows you to actively address any resistance or concerns regarding their shifting role.
Existing clients and their employees | Office Green customer | Participation: Acts as the core target audience and early testers of the new service. Resources: Critical user feedback, customer experience insights, and direct data on customer needs and pain points. | Impact on Needs: Provides a brand-new service to enhance their office environments, though interest levels will vary depending on individual client needs. Potential Resistance: Low risk overall. Lower-interest clients won't actively resist unless the launch is resource-draining or negatively impacts the existing product lines they currently pay for. | Medium (M) | Medium (M) | Frequency: Semi-regularly. Form: Semi-regular consultations, feedback surveys, and beta-testing check-ins. This keeps them informed about the upcoming service while leveraging their insights to improve the final user experience.
Office Green’s investors | Secondary stakeholder | uninvolved: Backs the project from a distance; uninvolved in day-to-day work but tracks overall launch success. Resources: Financial capital, funding resources, and long-term business backing. | Impact on Needs: Directly influences the financial performance and value of their investment in the company. Potential Resistance: None at this stage. They want the service to succeed financially and are completely hands-off prior to the launch. | Medium (M) | Low (L) | Frequency: Rarely (milestone-based). Form: Executive summary newsletters or high-level progress reports delivered monthly or quarterly. They only need to know that their investment is safe and on track for a successful launch.
Office Green’s receptionist | Office Green employee | Participation: Answers incoming client questions and routes inquiries closer to and after the official launch. Resources: Direct communication channel with customers, frontline service skills, and general company awareness. | Impact on Needs: Requires them to learn new product details and take on additional customer support/inquiry handling as the launch approaches. Potential Resistance: None. They currently have no concerns or opposition to the project. | Low (L) | Low (L) | Frequency: Rarely / Just-in-time. Form: A concise briefing memo and a short training session closer to the official launch date. They don't need ongoing details during development, just the essential facts right before they start handling customer inquiries.
Understanding stakeholders (stakeholder analysis)

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Prioritizing stakeholders (power grid)
OG Investors
Clients & Employees
OG Receptionist
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Interest
med
Landscape Designer/Web Designer
Director of Product

## Slide 3
Landscape Designer/Web Designer
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Director of Product
OG Investors
Clients & Employees
OG Receptionist
Interest
med
EXAMPLE
Prioritizing stakeholders (power grid)
Pro tip: You can move stakeholders higher or lower (or more to the left or right) within each box

## Slide 4
Landscape Designer/Web Designer
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Director of Product
OG Investors
Clients & Employees
OG Receptionist
Interest
med
EXAMPLE
Prioritizing stakeholders (power grid)
Pro tip: You can move stakeholders higher or lower (or more to the left or right) within each box
Director of Product

## Slide 5
Landscape Designer/Web Designer
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Director of Product
OG Investors
Clients & Employees
OG Receptionist
Interest
med
EXAMPLE
Prioritizing stakeholders (power grid)
Pro tip: You can move stakeholders higher or lower (or more to the left or right) within each box
Director of Product
Director of Product